## Cover Sheet
Risk Log
[Project Name]
Prepared by:
[Author] / [School/Division] / [Department]
[Status] – [Version] – [Date]

## Risk Log
[26 empty] | H | Yes
[26 empty] | M | No
L
N/A
[Project Name] - Risk Log
General Details | [5 empty] | Area of Impact |  |  | Exposure before Mitigation |  |  |  | Mitigation | [5 empty] | Exposure after Mitigation
Risk No. (Req'd) | Date Logged (Required) | Category (Optional) | Risk Description (Required) | Owner (Required) | Risk Status (Auto) | Impact on Schedule (Req'd) | Impact on Cost (Req'd) | Impact on Scope / Performance (Req'd) | Impact (1-10) 10=Major (Req'd) | Likelihood (1-10) 10=Certain (Req'd) | Used for Baseline Risk Graph only | Risk Rating (1-100) (Auto) | Mitigation Strategy (Required) | Mitigation Cutover Date (Required) | Mitigation Started? (Required) | Days Left (Auto) | No. of Days since Cutover Date (Auto) | Risk Closure Date (Required) | Impact (1-10) 10=Major (Req'd) | Likelihood (1-10) 10=Certain (Req'd) | Used for Current Risk Graph only | Risk Rating (1-100) (Auto) | Date Last Updated (Required) | Comments (Optional)
[5 empty] | 0 | [10 empty] | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Formulas:
Days Left (Auto) = IF([Risk Closure Date (Required)],0,IF([Mitigation Cutover Date (Required)]=TODAY(),"Today",AL8))
Note on C7: Select a category from the drop-down list. If you need to add another category, click on the Category column title. This is a hyperlink to the Category Setup table.
Note on D7: Enter the PRECISE details of the Risk ensuring it is quite clear as to what the Risk is.
Note on E7: Click on the drop-down list to select the Name of the person who will OWN the Risk.
Note on G7: Valid values are: H=High M=Medium L=Low N/A=Not Applicable
Note on H7: Valid values are: H=High M=Medium L=Low N/A=Not Applicable
Note on I7: Valid values are: H=High M=Medium L=Low N/A=Not Applicable
Note on J7: Valid values are 1 - 10. 1 - 4=Green 5 - 7=Yellow 8 - 10=Red
Note on K7: Valid values are 1 - 10. 1 - 4=Green 5 - 7=Yellow 8 - 10=Red
Note on L7: Valid values are 1 - 10. 1 - 4=Green 5 - 7=Yellow 8 - 10=Red
Note on M7: Valid values are 1 - 10. 1 - 35=Green 36 - 60=Yellow 61 - 100=Red
Note on O7: Enter the latest date that the mitigation strategy will need to kick in. In other words if the risk is REAL and Action has to be taken, this is the latest date it should start.
Note on P7: Select YES to indicate that mitigation has actually started, otherwise choose NO.
Note on Q7: Days Left: Today = Green 1-30 days = Yellow > 30 days = Normal text
Note on R7: Indicates the number of days since the cutover date that mitigation has been underway.
Note on T7: Valid values are 1 - 10. 1 - 4=Green 5 - 7=Yellow 8 - 10=Red
Note on U7: Valid values are 1 - 10. 1 - 4=Green 5 - 7=Yellow 8 - 10=Red
Note on W7: Valid values are 1 - 10. 1 - 35=Green 36 - 60=Yellow 61 - 100=Red
Note on Y7: Enter any relevant comments. For example if the Risk becomes an Issue, enter it on the Issues Log and record the Issue Number here.

## Risk Summary
[Project Name]
Risk Summary Metrics
| Summary of Open Risks by Risk Owner | [6 empty] | Number of Risks by Status |  |  |  | Breakdown of ALL Risks by Impact on Schedule
| Owner | No. of Open Risks | Total Exposure |  | No. of Open Risks with Cutover Date in the next 30 days | No. of Open Risks with Cutover Date in the next 31-60 days | No. of Open Risks where Mitigation is in progress
|  |  | Before Mitigation | After Mitigation
| 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | High
| 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Open |  |  |  | Medium
| 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Closed |  |  |  | Low
| 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | = | Total Risks |  | 0 | = | Risks Impacting Schedule
| 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | Number of Risks where Mitigation has been Necessary |  |  |  | Breakdown of ALL Risks by Impact on Cost
|  | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | High
|  | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Mitigation Necessary |  |  |  | Medium
|  | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Mitigation Unnecessary |  |  |  | Low
|  | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | = | Total Risks |  | 0 | = | Risks Impacting Cost
|  | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | Total Project Risk Rating for ALL Risks Before and After Mitigation |  |  |  | Breakdown of ALL Risks by Impact on Scope/Performance
|  | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Includes 'Open' and 'Closed' risks
|  | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | High
|  | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | Medium
|  | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Risk Rating before Mitigation |  |  |  | Low
|  | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Risk Rating after Mitigation
|  | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | = | Risks Impacting Scope/Perf.
|  | 0 | 0 | 0 | 0 | 0 | 0
| Total: | 0 | 0 | 0 | 0 | 0 | 0

## Setup Tables
Risk Log Setup Tables
Category | Names
Go to Risk Log - Category | Go to Risk Log - Owner
Note on D1: Help: You can enter up to 50 Names and 100 Categories in the columns on the left. Values entered here will dynamically update the corresponding drop-down lists on the 'Risk Log' worksheet. The Owner column within the table on the 'Risk Summary' worksheet will also dynamically update with any changes you make to the Names column on the left. Warning: If someone 'rolls off' the project, you MUST leave their name in the list to ensure accurate summary metrics. Any new additions to the team, should be added to the bottom of the list. You should NOT overtype an existing name with a new name. If you do, the old name will remain in any cells to which it has been assigned and the summary metrics will no longer be valid, since the names on the log have to be in the corresponding drop-down list. This goes for the Category columns too.

## Instructions Risk Log
Risk Log Instructions |  | User Interaction
1. | Risk No. - Enter the next number in the sequence. | REQUIRED
2. | Date Logged - Enter the date the Risk was added to the log - DD/MM/YY. | REQUIRED
3. | Categories are designed to be used as filters and are used in conjunction with the 'Auto Filter' feature in MS Excel. They are user-definable depending on your project requirements. Select a category from the drop down list (if you need to add to the drop down list, click on the column heading). | OPTIONAL
4. | Risk Description - Enter the precise details of the Risk ensuring it is quite clear as to what the risk actually is. | REQUIRED
5. | Owner - Select the name of the person who will own the Risk from the drop-down list. (If you need to add a new name, click on the Owner column heading.) | REQUIRED
6. | Risk Status - This is a self-calculating column so you MUST NOT try to enter anything. When a date is entered in the Date Logged cell, the status is set to 'New'. When a name is entered in the Owner cell, the status changes to 'Open' and when a date is entered in the Closure Date cell, the status changes to 'Closed'. | NO - AUTOMATIC
7. | Area of Impact - This is sub-divided into three areas, namely Schedule, Cost and Scope/Performance. Choose High (H), Medium (M), Low (L) or Not Applicable (N/A) from the drop-down list for each of these areas to indicate the impact the risk will have on them. | REQUIRED
8. | Impact if Not Received - Enter the PRECISE details of the Impact to the project if the RFI response is not received by the date required. Think in terms of Project Schedule, Cost, Scope, Quality and Performance. Where there is no impact type None. (E.g. A delay in receiving a response might mean a Functional Specification cannot be written by the deliverable date shown on the project plan.) | REQUIRED | ???
9. | Exposure Before Mitigation (Impact) - Enter a score of 1 to 10 to indicate the degree of Impact the risk has on the project prior to mitigation (10=Major). | REQUIRED
10. | Exposure Before Mitigation (Likelihood) - Enter a score of 1 to 10 to indicate how likely it is that the risk will impact the project prior to mitigation (10=Certain). | REQUIRED
11. | Exposure Before Mitigation (Risk Rating) - This is a self-calculating column so you MUST NOT try to enter anything. The Risk Rating = Degree of Impact X Likelihood. | NO - AUTOMATIC
12. | Mitigation Strategy - Enter details of how you intend to mitigate the risk. | REQUIRED
13. | Mitigation Cutover Date - Enter the date the Mitigation Strategy plan will need to commence so as to not jeopardise the project deadline. | REQUIRED
14. | Mitigation Started? - Select Yes or No from the drop-down list. | REQUIRED
15. | Day Left - This a self-calculating column so you MUST NOT try to enter anything. If the Mitigation Cutover Date is today, Days Left will show in GREEN. If there are 1-30 days before the Mitigation Cutover Date, Days Left will show in YELLOW. If there are more than 30 days until the Mitigation Cutover Date, Days Left will show as Regular text. | NO - AUTOMATIC
16. | No. of Days Since Cutover Date - This a self-calculating column so you MUST NOT try to enter anything. When the Mitigation Cutover Date is earlier than today's date the number of days since the cutover date will show in this cell. They will continue to show in the cell if the Risk Closure Date is after the Mitigation Cutover Date but will be frozen at that point. This then indicates the total days taken to mitigate the risk. | NO - AUTOMATIC
17. | Risk Closure Date - Enter the date the Risk is no longer a threat to the project - DD/MM/YY. | REQUIRED
18. | Exposure After Mitigation (Impact) - Enter a score of 1 to 10 to indicate the degree of Impact the risk has on the project prior to mitigation (10=Major). | REQUIRED
19. | Exposure After Mitigation (Likelihood) - Enter a score of 1 to 10 to indicate how likely it is that the risk will impact the project prior to mitigation (10=Certain). | REQUIRED
20. | Exposure After Mitigation (Risk Rating) - This is a self-calculating column so you MUST NOT try to enter anything. The Risk Rating = Degree of Impact X Likelihood | NO - AUTOMATIC
21. | Date Last Updated - Enter the date the Risk was last updated on the Risk Log - DD/MM/YY. | REQUIRED
22. | Comments - Enter any relevant comments. If the Risk becomes an Issue and is entered on the Issues Log, enter the respective Issue Number here so that they can be cross-referred. | OPTIONAL
Helpful Hints
1. | Adding Extra Rows - If you need to add a new line to the Risk Log - Choose Tools>Protection>Unprotect Sheet and click on OK. Do NOT just insert a new row, as this will not include the required formulae and therefore what you enter in the row will not be included in the calculations that feed the Risk Summary metrics. Instead, copy the previous line (Cntrl+C), press the right mouse button and choose 'Insert Copied Cells'. This will ensure all the formulae and formatting are copied to the new row. Protect the sheet again afterwards. You do not need to put in a password.
2. | Printing the Workbook - By default the page size of the Title Page, Risk Log and Risk Summary worksheets is A4. If you have access to an A3 printer, it is recommended that you print on this page size. Note: A3 will only be available for selection when you have a printer driver for an A3 printer selected. Also, before printing it is recommended that you filter on the Risk Status of 'Open' and set the Print Area to only include the rows that contain Open actions.
3. | Using the AutoFilter feature - Remove the Protection from the worksheet by choosing Tools>Protection>Unprotect Sheet and clicking on OK. Then select row 7 and choose Data>Filter>AutoFilter. A number of drop-down boxes will appear along this row. To filter out any closed Risks, choose 'Open' from the Risk Status drop-down box. To just show open Risks for a particular person, choose their name from the Owner drop-down box. Once printed, remove the AutoFilter by choosing Data>Filter>AutoFilter.

## Formulae (hidden)
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0